## Actuals - Weekly Log
Name | Team | Game | Week | Role (s) | Hours | Description (What you did) | Comments
Hema Chandra Reddy | Code Executioners | The Hangman | 1 | Developer | 4 | Understanding of the game and game play of The Hangman. Analysed the requirements of the game. Decided on team name, team lead and programming language to be used for development.
Kavya Rao | Code Executioners | Jumble | 1 | Customer | 4 | Gave requirements to game Jumble for the team All Jumbled Up. Gave ideas on how to develop the game like which programming language to be used.
Daniel Devos | Code Executioners | The Hangman | 1 | Developer | 6 | Setup production environment on AWS / Built Initial Prototype in Grails
Pallavi | Code Executioners | The Hangman | 1 | Requirements Engineer | 5 | Gathered requirements from the team The Mighty Icicles for the game The Hangman and documented the same.
Hema Chandra Reddy | Code Executioners | The Hangman | 2 | Requirements Engineer | 6 | Negotiated the requirements of the game The Hangman with the customer like which are feasible for development and resolved all the ambiguous requirements with the customer. | Need to do some research on Grails to work with Dan on the project.
Kavya Rao | Code Executioners | The Hangman/Jumble | 2 | Developer/Customer | 6 | Clarified all the requirements regarding the game Jumble for the team All Jumbled Up. Reviewed the working high level application of Jumble as part of game iteration 1. Worked on how to develop the requirements received from customer for The Hangman in grails using Java. | Need to do some research on Grails and need to give some clarity of the game play to team All Jumbled Up.
Daniel Devos | Code Executioners | The Hangman | 2 | Developer | 6 | Researched on how to establish a connection between our application and a database server for data retrieval and data manipulation and saving. | Need to gather more information on establishing DB connection between AWS dynamoDB.
Pallavi | Code Executioners | The Hangman | 2 | Requirements Engineer | 6 | Negotiated the requirements of the game The Hangman with the customer like which are feasible for development and resolved all the ambiguous requirements with the customer. | Need to create a github user ID and install the same on the machine.
Hema Chandra Reddy | Code Executioners | The Hangman | 3 | Developer/Requirements Engineer | 6 | Created a GitHub repository for the team to work on the project. Worked on implementing the key logic of the game play in Java. We as a team had a meeting and noted down all to do items for the next week. Worked on creating a charter for the game Hangman to resolve all ambiguity in the requirements. | Need to give a walkthrough of Github to some new users on the team.
Kavya Rao | Code Executioners | The Hangman | 3 | Developer/Requirements Engineer | 6 | Researched on how to establish a connection of Amazon DynamoDB with our application. Was responsible for working on the charter with the requirements of Hangman. | Need to get some hands on with the github and Grails.
Daniel Devos | Code Executioners | The Hangman | 3 | Developer/Requirements Engineer | 6 | Was responsible for creation of webpage on a high level for the game. Responsible for negotiating the requirements of exact gameplay with the customer for Hangman. | Need to do some research on integrating our application with the third party APIs like facebook, twitter, etc.
Pallavi | Code Executioners | The Hangman/Jumble | 3 | Developer/Customer | 6 | Clarified some of the requirements which are unclear for the game Jumble and researched on some of the web designing aspects in Java. Was responsible for drafting a risk assessment document for our project. | Need to get some hands on with the github and Grails.
Hema Chandra Reddy | Code Executioners | The Hangman | 4 | Developer | 8 | Designed the tables for our project and inserted the data into the same. Also done some investigation on how to establish a database connection with grails for our project. Wrote some of the logic for meeting some requirements of the game. | I need to revisit the design of the project with our teammates.
Kavya Rao | Code Executioners | The Hangman | 4 | Developer | 8 | Worked on developing the core logic of the game Hangman. Designed the login page for the application. | Need some more specifics on the look and feel of the user interface from the customer's perspective.
Daniel Devos | Code Executioners | The Hangman | 4 | Developer | 8 | Worked on the main logic of the application meeting some of the requirements.
Pallavi | Code Executioners | The Hangman | 4 | Developer/Customer | 8 | Worked on implemeting some of the screens for our application. Also gave clarifications in the requirements of the game Jumble as a customer. | The screens developed need to get reviewed by the customer.
Hema Chandra Reddy | Code Executioners | The Hangman | 5
Kavya Rao | Code Executioners | The Hangman | 5
Daniel Devos | Code Executioners | The Hangman | 5
Pallavi | Code Executioners | The Hangman | 5
Hema Chandra Reddy | Code Executioners | The Hangman | 6
Kavya Rao | Code Executioners | The Hangman | 6
Daniel Devos | Code Executioners | The Hangman | 6
Pallavi | Code Executioners | The Hangman | 6
Hema Chandra Reddy | Code Executioners | The Hangman | 7
Kavya Rao | Code Executioners | The Hangman | 7
Daniel Devos | Code Executioners | The Hangman | 7
Pallavi | Code Executioners | The Hangman | 7
Hema Chandra Reddy | Code Executioners | The Hangman | 8
Kavya Rao | Code Executioners | The Hangman | 8
Daniel Devos | Code Executioners | The Hangman | 8
Pallavi | Code Executioners | The Hangman | 8
Hema Chandra Reddy | Code Executioners | The Hangman | 9
Kavya Rao | Code Executioners | The Hangman | 9
Daniel Devos | Code Executioners | The Hangman | 9
Pallavi | Code Executioners | The Hangman | 9
Hema Chandra Reddy | Code Executioners | The Hangman | 10
Kavya Rao | Code Executioners | The Hangman | 10
Daniel Devos | Code Executioners | The Hangman | 10
Pallavi | Code Executioners | The Hangman | 10
Hema Chandra Reddy | Code Executioners | The Hangman | 11
Kavya Rao | Code Executioners | The Hangman | 11
Daniel Devos | Code Executioners | The Hangman | 11
Pallavi | Code Executioners | The Hangman | 11
Hema Chandra Reddy | Code Executioners | The Hangman | 12
Kavya Rao | Code Executioners | The Hangman | 12
Daniel Devos | Code Executioners | The Hangman | 12
Pallavi | Code Executioners | The Hangman | 12
Hema Chandra Reddy | Code Executioners | The Hangman | 13
Kavya Rao | Code Executioners | The Hangman | 13
Daniel Devos | Code Executioners | The Hangman | 13
Pallavi | Code Executioners | The Hangman | 13
Hema Chandra Reddy | Code Executioners | The Hangman | 14
Kavya Rao | Code Executioners | The Hangman | 14
Daniel Devos | Code Executioners | The Hangman | 14
Pallavi | Code Executioners | The Hangman | 14
Hema Chandra Reddy | Code Executioners | The Hangman | 15
Kavya Rao | Code Executioners | The Hangman | 15
Daniel Devos | Code Executioners | The Hangman | 15
Pallavi | Code Executioners | The Hangman | 15
Hema Chandra Reddy | Code Executioners | The Hangman | 16
Kavya Rao | Code Executioners | The Hangman | 16
Daniel Devos | Code Executioners | The Hangman | 16
Pallavi | Code Executioners | The Hangman | 16

## Estimate to Completion
Name | Team | Game | Individual Estimate((Total hours to complete)) | Team Estimate (Total hours to complete) | Week | Comments
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble | 380 - 420 | 416 | 1 | On an average each member on the team need to spend around 6 -7 hours a week for successful project completion.
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble | 384 | 416 | 1 | I felt like each person can work for 6 hours a week on the project.
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble | 370 - 400 | 416 | 1 | After analysing the game play of Hangman, I felt like each person on the team can spend 5 - 6 hours a week on the project.
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble | 448 | 416 | 1 | Considering the experience of the people on the team and the game complexity, I felt like each individual on team need to spend more than six hours a week on the project.
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble | 360 | 374 | 2 | After knowing the requirements of the game Hangman from the customers, I felt like spending 5 hours a week on the project is enough for successful completion.
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble | 350 - 370 | 374 | 2 | After getting the requirements from our customer I felt like reducing the estimates which I gave earlier.
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble | 360 | 374 | 2 | With the requirements given by the customer, I reduced my estimates previously given.
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble | 400 | 374 | 2 | As I am new to programming, I gave higher estimates previously to cope with team and now I am making a good progress with the help of the team.
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble | 380 | 380 | 3 | We as a team decided to develop the game in Java using Grails framework. To get ease with this I increased my estimate from previos week.
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble | 350 - 370 | 380 | 3
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble | 360 | 380 | 3
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble | 400 | 380 | 3
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble | 380 | 380 | 4
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble | 350 - 370 | 380 | 4
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble | 360 | 380 | 4
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble | 400 | 380 | 4
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 5
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 5
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 5
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 5
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 6
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 6
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 6
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 6
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 7
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 7
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 7
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 7
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 8
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 8
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 8
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 8
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 9
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 9
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 9
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 9
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 10
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 10
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 10
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 10
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 11
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 11
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 11
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 11
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 12
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 12
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 12
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 12
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 13
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 13
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 13
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 13
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 14
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 14
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 14
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 14
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 15
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 15
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 15
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 15
Hema Chandra Reddy | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 16
Kavya Rao | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 16
Daniel Devos | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 16
Pallavi | Code Executioners | Developers: For Hangman Customers: For Jumble |  |  | 16